ANEXA LA HOTĂRÂREA CONSILIULUI LOCAL AL MUNICIPIULUI CRAIOVA NR.201/2020

Milano, 11th May 2020

Bilateral Partnership Agreement between

Città metropolitana di Milano

and

Consiliul Local al Municipiului Craiova

PARTNERSHIP AGREEMENT

between

Città metropolitana di Milano

represented by its

LEAR – Legal Entity Appointed Representative Mr Carmine Pacente

and

Consiliul Local al Municipiului Craiova

represented by  its

Mayor Mr Mihail Genoiu

This Convention must be sent to the Città metropolitana di Milano duly signed and in duplicate copy.

PREAMBLE

Whereas:

- The Parties have submitted to the European Commission the Project entitled CAMELOT: Cities And Metropolis in Europe Labouring Onward Together under the Europe for Citizens program, Strand 2 – Democratic engagement and civic participation / Action 2.2 - Networks of Towns;

- The Project has been approved and Grant Agreement Nr. 615289 has been signed between the EACEA (The Education, Audiovisual and Culture Executive Agency) and Città metropolitana di Milano (Hereinafter the “Beneficiary”) for the implementation of the Project;

- The Beneficiary has, among the priorities of its strategy the promotion of the process of economic, social and cultural integration of the European Union, in particular through the coordination among European cities and metropolitan areas and the EU institutions with a real involvements of citizens in the decision making process.

- Consiliul Local al Municipiului Craiova has, among the priorities of its strategy the encouragement of democratic and civic participation of citizens at Union level, by developing citizens' understanding of the Union policy making-process and promoting opportunities for social and intercultural engagement and volunteering at Union level.

- Consiliul Local al Municipiului Craiova (Hereinafter the “Partner”) is an official partner within the project CAMELOT.

The Parties wish to specify or supplement, between themselves, the provisions of the Bilateral Partnership Agreement;

Now, therefore, it is hereby agreed as follows:

By signing the Bilateral Partnership Agreement, the Partner accepts the grant and agrees to implement it under its own responsibility and in accordance with the Bilateral Partnership Agreement, with all the obligations and conditions it sets out.

Article 1 – Duration of the Partnership Agreement

This Partnership Agreement is valid from 2nd of March 2020 to 28th February 2022. The period 2nd March – 28th February 2022 is due to the correct submission of the final report to which the Partner shall contribute (See Article 4).

Article 2 – The object of the Partnership Agreement is the “Implementation of the project CAMELOT”

The Partner shall implement and assist in the implementation of all the activities as defined in Annex 1 (“Action plan”) within the overall implementation of the CAMELOT project and the list of tasks and roles detailed in Annex 1, in a spirit of cooperation and good faith.

  - Article 3 – Compensation

The Beneficiary financially supports the Partner for the implementation of the project, as described in the Annex B, with 10.000,00 Euros.

The first instalment between 40% and 60% of the total amount will be submitted after signature of the Partnership Agreement and upon request for payment (see Annex C).

The final rest of settlement will be paid following the Beneficiary’s receipt of the final balance by the European Commission (EC). Any expenses’ cuts by the EC would not be able to be paid.

Article 4 – Report and supervision

- The Partner, without additional call, shall provide the Beneficiary with any information and documents essential for preparing the Final report.

- Irrespective of the obligation mentioned in 4.a., the Partner on the Beneficiary’s demand is obliged to make other usual information and documents available for the Beneficiary in relation to the project performance.

- The Partner is obliged to provide the Beneficiary with all information and documents which are regarded as essential for evaluating the level of project realisation.

- To the extent determined in 4.a-c, the Partner is obligated to participate actively in the monitoring carried out by the EACEA, the European Commission or the Audit Board within the financial or operational audit to be carried out at the presence of the Partner. The obligation corresponding to the preceding sentence binds the Partner within the contract duration and within 5 years after its termination.

- The acceptance of the Final Report is conditioned upon the publication of the project-related information on the website of the Partner: in order to receive the payment of the grant the Partner must publish on its website (under the responsibility of the legal representative) the information containing the details on the implemented project (i.e. place and dates of the events, number of participants in the events per Country, brief description of the activities). The Final Report must clearly indicate the link to the Partner’s website allowing having access to the posted information. This information must be available on the website of the Partner for 6 months upon the accomplishment of the project (Annex D – Template to be used).

    - Article 5 – Termination of the Partnership Agreement

The signatories may terminate the contract by giving 30 days’ notice if the activities are not implemented following the action plan proposed.

The Beneficiary may also suspend the payment of balance or request the reimbursement of the first instalment, should the Partner not be fulfilling its obligations. In the case of presentation of not satisfactory reports in due time, the Beneficiary reserves the right to demand the reimbursement of the instalments previously provided.

Article 6 – Visibility and communication

Any communication activity related to the action (including in electronic form, via social media, etc.) and any infrastructure, equipment and major results funded by the grant must:

- display the logo of the project;

- display the logo of Città metropolitana di Milano;

- display the logo of Consiliul Local al Municipiului Craiova;

- display the “Europe for Citizens” logo.

Use of signs and posters: whenever the action includes events for the public, signs and posters related to this action shall be displayed. This shall include the logos listed under points a-d.

The Partner shall use the templates provided by the Beneficiary with regards to CAMELOT related activities and shall promote the project and disseminate its outputs throughout its network. It shall also provide the Beneficiary with all the necessary information concerning related-activities and outputs for their dissemination (through online and non-online when foreseen) means.

Article 7 – Settlement of disputes

The present agreement has been drafted in accordance with international legal rules and the Milan Court shall have jurisdiction in any disputes between the parties.

The present convention is drafted in 2 identical copies in English language.

| Città metropolitana di Milano Mr. Carmine Pacente | Consiliul Local al Municipiului Craiova Mr. Mihail Genoiu |
| --- | --- |

Annex A: Action plan

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 02/03/2020 - 31/03/2020 | Preparation activities | All partners |
| Detail activity: Activity 1 | During the first month of the project, the partners will discuss the action plan of the project and the technical and practical aspects of the project implementation, including the organization and timing of local activities. |  |
| Tasks and Responsibilities | - The Partner will participate and contribute to the preparation activities. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 02/03/2020 - 28/02/2022 | Website creation | Online |
| Detail activity: Activity 2 | A website in English will be realised at the beginning of the project. It will be used during the whole duration of the project and possibly beyond it, to share documentation on civic participation in local governance, on the project's activities and to inform on best practices. The cities partners will actively participate in the maintenance of the website, providing relevant documentation on local activities and international seminars. |  |
| Tasks and Responsibilities | - The Partner will contribute to the development of the project website. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 02/03/2020 - 31/03/2020 | Questionnaire | All partners |
| Detail activity: Activity 3 | A questionnaire will be prepared by the project partners in order to assess the knowledge of participants and to estimate the sense of belonging towards the European institutions. They will take into consideration the variety of actors involved and will be adapted to the type of events that will take place as well as the topics covered by the events. There will be two versions. One will be distributed before the targeted event and the other at the end. |  |
| Tasks and Responsibilities | - The Partner will contribute to the development of the questionnaire. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 02/03/2020 - 28/02/2022 | Local activities | All partners |
| Detail activity: Activity 4 | Each metropolitan city will organize and host participative local activities, that will involve citizens. They will be a place to discuss one of more or the topics of the international conferences, and will gather around 25 participants of status (youth, policy makers, foreigners living in the metropolitan areas, etc.), with the aim to actively involve them in the decision making process of metropolitan cities. |  |
| Tasks and Responsibilities | - The Partner will organise the local event. Please note: In order to be eligible the event must directly involve at least 25 participants. Please note: In order to be eligible the event must last at least 1 working day. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 10/2020 - 10/2020 | International event: 18th European Week of Regions and Cities – Empowering citizens “Eu funds to contrast COVID-19 emergency” | Brussels, Belgium |
| Detail activity: Activity 5 | The European Week of Regions and Cities is an annual four-day event during which cities and regions showcase their capacity to create growth and jobs, implement European Union cohesion policy, and prove the importance of the local and regional level for good European governance. |  |
| Tasks and Responsibilities | - The Partner sends 1 participant to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 11/2020 – 11/2020 | International event: “European instruments regarding the development of the metropolitan dimension” | Stuttgart, Germany |
| Detail activity: Activity 6 | Due to urbanization, cities continue to spread and interact with its surrounding areas. Europe’s future highly relies on the sustainable development of these functional urban areas. Therefore, we would like to focus on European instruments that support the dimension of European metropolitan regions. Special emphasis will be given to the revision of the EU territorial agenda and the development of a new Leipzig Charta during the German EU Council Presidency. |  |
| Tasks and Responsibilities | - The Partner sends 2 participants to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 02/2021 - 02/2021 | International event: “Management of the European funds and opportunities for metropolitan areas in the new MFF 2021 - 2027 - A debate on the future of Europe” | Milan, Italy |
| Detail activity: Activity 7 | The event will focus on what it would be the best method to manage the European funds in the metropolitan areas. The debate will be concentrated on how the European funds can be used, and especially on how important they can be to improve the life of citizens. Participants will be included in the discussion on what kind help the European funds can give to the Metropolitan authorities and to its citizens. |  |
| Tasks and Responsibilities | - The Partner sends 2 participants to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 03/2021 - 03/2021 | International event: “ITI instrument for the Urban Agglomeration” | Zagreb, Croatia |
| Detail activity: Activity 8 | The City of Zagreb will organize and host the international event related to the EU territorial instruments aimed for fostering development of the metropolitan areas since the City of Zagreb plays the role of the Intermediary Body for the ITI instrument for the Urban Agglomeration of Zagreb. The aim of the event it to raise awareness on the importance of the ITI mechanism for development of metropolitan areas and initiate debates on the project of key importance. |  |
| Tasks and Responsibilities | - The Partner sends 2 participants to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 05/2021 - 05/2021 | International event: “Metropolitan Areas and ITI - Integrated Territorial Investments” | Porto, Portugal |
| Detail activity: Activity 9 | AMP will organize and host the international conference “Metropolitan Areas and ITI - Integrated Territorial Investments". Policy-makers, metropolitan governments, public institutions, stakeholders, local actors and citizens will debate and present some good practices. The event would be attended by international participants as well as local ones. |  |
| Tasks and Responsibilities | - The Partner sends 2 participants to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 07/2021 - 07/2021 | International event: “Capitalization of ESIF projects of urban and metropolitan governments and citizens involvement” | Barcelona, Spain |
| Detail activity: Activity 10 | AMB will organize a seminar on capitalization of ESIF projects in urban and metropolitan territories in order to present the programs and to promote and increase citizen participation within these projects. Besides local stakeholders and Camelot partners we'll invite the European Commission, the managing authority of the ERDF OP for Catalonia. We'll aim at creating a link between this activity with the local action group of the RiConnect URBACT project (Metropolitan government of Porto is a partner). |  |
| Tasks and Responsibilities | - The Partner sends 2 participants to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 10/2021 – 10/2021 | International event: “Smart Metropolis” | Gdańsk, Poland |
| Detail activity: Activity 11 | The Smart Metropolis Congress is an annual international conference which creates a space where: 1. local governmental decision makers are identifying the challenges on the metropolis issues (f.e. how to find the optimal way of communication between decision makers of the metropolitan, regional and state level) in simple language, 2. influential and recognizable politicians (such as Robert Biedron, former Mayor of the city of Słupsk) are involved 3. current problems that are vital in nationwide perspective are discussed (f.e. role of small towns in the metropolises) 4. journalists and influencers are convinced to support metropolitan initiatives, 5. metropolises are shown as the laboratories of knowledge, ideas and good practice, including implementation EU and international projects. 6. novelties in governance/new trends in managing the metropolitan areas are presented. |  |
| Tasks and Responsabilities | - The Partner sends 2 participants to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 11/2021 - 11/2021 | International event: “The role of culture in European relations” | Bari, Italy |
| Detail activity: Activity 12 | In the current global context, the European cultural model, which consists of the diverse cultures that shape it, is often considered a benchmark to refer to. The Metropolitan City of Bari intends to launch a forum and offer a platform for discussion focusing on the following issues: cultural Heritage; European Cultural Relations. The main institutions and experts from both public and private sector will be involved, as well as universities, practitioners and civil society organisations. |  |
| Tasks and Responsibilities | - The Partner sends 2 participants to the event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 01/2022 - 01/2022 | International event: “Democratic engagement and civic participation” | Craiova, Romany |
| Detail activity: Activity 13 | The Municipality of Craiova will host the international event “Democratic engagement and civic participation” through local activity groups where policy-makers, public institutions etc. and citizens will share experiences and best practices for local government decisions. |  |
| Tasks and Responsibilities | - The Partner will organise the international event. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 02/03/2020 - 28/02/2022 | Documentary production | Milan |
| Detail activity: Activity 14 | A documentary will be shot during the duration of the project, presenting the various partners and their initiatives for civic participation. It will focus on the debates carried out at local level and during the international seminars. It will present the results obtained during the project and it will be disseminated during the final event. It will also be accessible directly from the website of the project. |  |
| Tasks and Responsibilities | - The Partner will contribute to the production of the video according to the guidelines developed by the coordinator. |  |

| Date | Type of activity | Venue of the activity |
| --- | --- | --- |
| 02/03/2020 - 28/02/2022 | Publication production | Online |
| Detail activity: Activity 15 | A publication will be elaborated and disseminated to the project participants and it will also be available directly on the project website. This publication will present the results of the project and local events. |  |
| Tasks and Responsibilities | - The Partner will contribute to the production of the publication according to the guidelines developed by the coordinator. |  |

Annex B: Budget

| ITEMS | Unit type | Unit cost | Unitary number | TOTAL |
| --- | --- | --- | --- | --- |
| International event in Craiova (Activity 13) |  |  |  |  |
| 1.1 Accommodation for international participants | Per pax | 170 | 17 pax * 2 nights | € 2.040,00 |
| 1.2 Meals for international participants | Per pax | 140 | 17 pax * 2 lunch and 2 dinner | € 1.700,00 |
| 1.3 Event coordination and materials | Per event |  | 1 | € 1.480,00 |
|  |  |  | Sub-total | € 5.220,00 |
| Travel costs for the international events (Activities 6, 7, 8, 9, 10, 11, 12) |  |  |  |  |
| 2.1 Round-trip tickets travel for 2 delegates | Per pax | 270 | 2 pax * 7 events | € 3.780,00 |
|  |  |  | Sub-total | € 3.780,00 |
| Local Activity (Activity 4) |  |  |  |  |
| 2.1 Organisation of the local activity | Lump sum | 1000 | 1 | € 1.000,00 |
|  |  |  | Sub-total | € 1.000,00 |
| TOTAL |  |  |  | € 10.000,00 |

The following additional costs will be covered by the project:

- Accommodation, board and all other direct costs for the international events (Activities 5, 6, 7, 8, 9, 10, 11, 12) are covered directly by the event organiser.

Annex C: template request for payment

Città metropolitana di Milano

Via Vivaio 1

20122 Milano

Italy

MUNICIPIUL CRAIOVA

PRIMĂRIA MUNICIPIULUI CRAIOVA

Str. A.I. Cuza, Nr. 7     Tel.: 40251/416235

Craiova, 200585  Fax: 40251/411561

consiliulocal@primariacraiova.ro

www.primariacraiova.ro

Subject: Request for payment - Project CAMELOT

Hereby we kindly ask you the advance of Euros as first instalment for the activities that City of Zagreb as a project partner, will implement within the project CAMELOT (Cities And Metropolis in Europe Labouring Onward Together).

| Date | Description of expenditures | Amount in Euro |
| --- | --- | --- |
|  | First instalment (60%) – implemetation of project activities CAMELOT | € 6.000,00 |
|  | Total amount | € 6.000,00 |

at the following bank account:

BANK DETAILS here

Best regards,

11th May 2020

Consiliul Local al Municipiului Craiova

Mayor Mr Mihail Genoiu

Annex D – Template for the website

| The project « CAMELOT» was funded with the support of the European Union under the Programme "Europe for Citizens" |  |  |  |
| --- | --- | --- | --- |
| Applicable to the Strand 2.2 – "Networks of Towns" |  |  |  |
| 8 events have been carried out within this project: Event 1 Participation: The event involved ... citizens, including .... participants from the city of ... (country), .... participants from the city of .... (country) etc. Location / Dates: The event took place in ... (city, country), from dd/mm/yyyy to dd/mm/yyyy Short description: The aim of the event was ….. Event 2 Participation: The event involved ... citizens, including .... participants from the city of ... (country), .... participants from the city of .... (country) etc. Location / Dates: The event took place in ... (city, country), from dd/mm/yyyy to dd/mm/yyyy Short description: The aim of the event was ….. Event 3 Participation: The event involved ... citizens, including .... participants from the city of ... (country), .... participants from the city of .... (country) etc. Location / Dates: The event took place in ... (city, country), from dd/mm/yyyy to dd/mm/yyyy Short description: The aim of the event was ….. Event 4, 5, etc. |  |  |  |

PREȘEDINTE DE ȘEDINȚĂ,

Adrian COSMAN